## PIF
A. | PROJECT INFORMATION
1 | Project Title: |  |  | Castro Mobile Home Park Water Consolidation
2 | Project Sponsor(s): |  |  | Coachella Water Authority
3 | Eligible Applicant Type:
4 | IRWM Project Region(s): |  |  | Coachella Valley Regional Water Management Group
5 | Does the project provide benefits directly to a Disadvantaged Communities (DAC) and/or Economically Distressed Areas (EDA) (minimum 75% by population or geography)?
|  | Yes | No | If yes, please complete D.8 and/or D.9. Show on map if applicable.
6 | Is the Project Sponsor a Tribe, or does the project provide benefits to a Tribe (minimum 75% by population or geography) as defined by Proposition 1?
|  | Yes | No | If yes, please complete D.10. Show on map if applicable.
7 | Provide project map. Include location of project, project benefit and/or service area, and other applicable information.
8. Funding Category:
DAC Implementation Project
General Implementation Project
9. Project Type: | [5 empty] | Other: | water consolidation
Select most applicable project type. See Section II.C. of the 2019 Guidelines for full description of eligible project types. If "Other" is selected, please write in the space provided the proposed project type.
B. | SELECTED ELIGIBILITY REQUIREMENTS
1 | Will the project be included in the IRWM Plan, that will be adopted prior to anticipated Agreement Execution?
|  | Yes | No
2 | Does the project address a critical need(s) and/or priority(ies) of the IRWM Region as identified in the IRWM Plan?
|  | Yes | No | If yes, complete part a:
a. | What IRWM Plan goal(s)/objective(s) does the project address? Identify and explain.
Objective A: Provide reliable water supply. This project provides a reliable water supply by consolidating the mobile home park a system with a failed groundwater well serving a severely DAC to the Coachella Water Authority (CWA) potable water system. Objective J: Maximize stakeholder involvement. CWA has been in contact with various DACs in and around its service area, including the owners of the Castro Mobile Home Park (MHP). This project is a result of continued stakeholder involvement. Objective L: Address water and sanitation needs of DACs. This project will provide a reliable and safe water supply by consolidating the Castro MHP's small water system; a system with a failed groundwater well serving a severely DAC to the CWA potable water system. Objective M: Maintain affordability of water. By consolidating the Castro MHP's system to the bigger municipal public water system, customers would be paying more affordable water rates. Objective B: Manage groundwater levels and Objective E: Protect groundwater quality are also addressed - see Attachment 4 Work Plan.
3 | Does the project have an expected useful life consistent with Government Code §16727 (generally 15 years)? If not, explain why this requirement is not applicable.
The anticipated life cycle of a ductile iron pipeline and its appurtenances is projected to be well over 50 years, based on historical data provided by several pipeline manufacturers and studies.
4 | Does the project address and/or adapt to the effects of climate change? Does the project address the climate change vulnerabilities assessed in the IRWM Plan?
|  | Yes | No | If yes, please explain below.
In Chapter 3 of the 2018 Coachella Valley IRWM/SWR Plan Update, the Region created models to project climate change impacts to water supplies and infrastructure. Generally, climate change is expected to increase temperatures, with little to no change in average rainfall, and increase in water demand due to higher irrigation needs caused by increased temperatures. This project directly addresses medium priority vulnerabilities related to “Water Demand: Limited ability to meet summer demand” by improving access to safe drinking water and abandoning inefficient small system wells that depend on recharge water. Local conveyance is a “no regret” strategy that helps to both adapt to climate change and mitigate GHG emissions. By consolidating small systems into larger water systems, it provides local residents with clean, safe, affordable and reliable drinking water that they typically would not be able to obtain. As more small systems get consolidated into the larger systems, water loss and groundwater contamination associated with poorly maintained wells will be reduced. This project allows the Region to better regulate water usage by reducing the number of extraction points throughout the basin. The consolidation of these smaller systems will help better manage the basin’s water supply.
5 | Does the project contribute to regional water self-reliance?
|  | Yes | No | If yes, please explain below.
This project provides a safe reliable water supply to disadvantaged community whose groundwater well has severely deteriorated casing and no longer can provide safe drinking water without significant repairs. The well has a hole in the upper casing that allows shallow groundwater to enter the well. Prior to the casing failure, the well met drinking water standards. However, with the intrusion of shallow groundwater, the well now has hexavalent chromium over the proposed state maximum contaminant level (MCL) of 10 micrograms per liter.
6 | Does the project provide a benefit that meets at least one of the Statewide Priorities as defined in the 2019 IRWM Grant Program Guidelines?
|  | Yes | No | If yes, please identify below.
7 | Will CEQA be completed within 12 months of Final Award?
Yes
NA, project is exempt under CEQA
NA, not a project under CEQA
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
8 | Will all permits necessary to begin construction be acquired within 12 months of Final Award?
Yes
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
C. | WORK PLAN, BUDGET, and SCHEDULE SUMMARY
1 | Project Description: Provide a brief project description summarizing major components, objectives, goals, and intended outcomes/benefits (quantitative and qualitative).
The Castro Mobile Home Park (MHP) has been connected to Coachella Water Authority (CWA) through a temporary highline since February 2017. The project consists of installation of approximately 830 linear feet of 8-inch water main, approximately 45 water services, meter boxes and service reconnections. Once the proposed water main is approved for service and connection to the MHP service connections, the existing water well will be destroyed per California Department of Water Resources standards and Riverside County Department of Environmental Health requirements. The water main, water services and meter boxes will be owned and operated by CWA; however, these facilities will be located on private property owned by the MHP. The project would extend the CWA water main from the two nearest points of connection and would extend approximately 840 feet within the MHP site. Fire hydrants would be installed and spaced to meet fire department requirements as well. Water services would be constructed to each of the tenant spaces would be placed. These water services would include the installation of a water meter box and water meter to each of the tenants is required by CWA. A water line from the meter box to the service connection pad and to each unit would be installed to finalize and complete connection to each trailer. 90% design plans are complete as of September 2019 by MSA Consulting and a Notice of Exemption for CEQA will be completed by December 31, 2019. The objective of the project is to provide Castro MHP a reliable safe potable water source by consolidating the existing small water system with the CWA system. Alternatives evaluated in 2017 included repairing the existing well, replacing the existing well and consolidating with the CWA potable water system. However, the cost to repair and/or replace the well and the associated ongoing operation and maintenance of the well and deteriorating distribution system would have been difficult for the MHP residents to afford. Consolidating into the larger CWA system reduces the costs to residents for safe reliable drinking water.
2 | Budget: Provide cost estimates for each Budget Category listed in the table below. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 1 - Project Budget
Category |  |  | (a) |  | (b) |  | (c) | (c) | (d)
|  |  | Cost Share: Non‐ State Fund Source |  | Requested Grant Amount |  | Other Cost Share (including other State Sources) |  | Total Cost
(a) | Project Administration |  | 0 |  | 28097 |  | 6868 |  | 34965
(b) | Land Purchase/ Easement |  | 0 |  | 0 |  | 4000 |  | 4000
(c) | Planning/Design /Engineering /Environmental Documentation |  | 0 |  | 14680 |  | 16936 |  | 31616
(d) | Construction/ Implementation |  | 0 |  | 1056468 |  | 14040 |  | 1070508
(e) | Grand Total (Sum rows (a) through (d) for each column) |  | 0 |  | 1099245 |  | 41844 |  | 1141089
Note: Provide information or other documentation to support the cost estimate in a separate attachment. Identify the source of all cost share and other funds. If other funds are not used, describe efforts to obtain other funding and/or why other funding sources were not used.
Castro MHP serves a severely DAC system and has a continuing unaddressed need to resolve its water system deficiencies. This project is requesting a cost share waiver due to the communities small severely DAC status. For other cost share, CWA will pay consulting fees for completion of the design, the easement preparation, and CEQA documentation. CWA will also provide CWA staff labor for completion of the reporting, and for portions of the contract services and construction administration.
3 | Cost Share Waiver Requested (DAC or EDA)? |  |  |  |  | Yes | No | If yes, continue below:
Cost Share Waiver Justification: Describe what percentage of the proposed project area encompasses a DAC/EDA, how the community meets the definition of a DAC/EDA, and the need of the DAC/EDA that the project addresses. In order to receive a cost share waiver, the applicant must demonstrate that the project will provide benefits (minimum 25% by population or geography) that address a need of a DAC and/or EDA.
Almost the entire City of Coachella and Coachella Water Authority service area is comprised of DAC's, with some areas that qualify as severely DAC's (SDACs). Castro MHP is categorized as 100% DAC by geography and as it serves less than 10,000 persons is also categorized as a small DAC. Per DWR's DAC Mapping Tool, the median household income in the 2016 tract that includes Castro MHP is $31,615, which is less than 60% of the statewide MHI of $38,272 and thus qualifies Castro MHP as a severely DAC. The project will provide safe and reliable drinking water and proper fire protection to the MHP residents.
4 | Schedule: Include reasonable estimates of the start and end dates for each Budget Category listed in Table 1 - Project Budget. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 2 - Project Schedule
Category |  |  |  |  | (a) Start Date |  |  | (b) End Date
(a) | Direct Project Administration |  |  |  | 2020-04-15 |  |  | 2021-02-08
(b) | Land Purchase/ Easement |  |  |  | 2020-01-01 |  |  | 2020-02-29
(c) | Planning/Design/Engineering/Environmental Documentation |  |  |  | 2019-11-01 |  |  | 2020-08-18
(d) | Construction/ Implementation |  |  |  | 2020-04-15 |  |  | 2020-12-08
D. | OTHER PROJECT INFORMATION
1 | Provide a narrative for project justification. If applicable, include references to supporting documentation such as models, studies, engineering reports, etc. Include any other information that supports the justification for this project, including how the project can achieve the claimed level of benefits.
Castro MHP is located within the City of Coachella and within the existing water system service area. However, Castro MHP was not connected to the CWA water system and relied on its own well and was regulated as a small public water system by Riverside County Department of Environmental Health (DEH). As of DEH’s 2017 Small Water System Permit and Inspection Report, the MHP’s well was a 600-foot-deep well with a 3 horsepower (hp) submersible pump located on Tyler Street. The well was drilled in 1958 and pumped approximately 50 gallons per minute (gpm). The well pumped to a 1500 gallon hydropneumatic tank, then out into the MHP distribution system. The DEH Inspection Report notes a 2015 Water Quality Emergency Notification Plan and 2015 Bacteriological Sample Siting Plan, evidence of a long history of water quality contamination in this DAC. Coliform bacteria sampling was not satisfactory, and a Citation and Compliance Order (No. 05_63_16C_025) was issued to Castro MHP in October 2016. The DEH Inspection Report further explains that the well casing was severely deteriorating near the base of the well casing. There were small holes in the well casing where the casing and ground met. The operator applied duct tape over the holes at the time of the inspection, but the well casing was a source of contamination. There was also a leaking pressure relief valve located near the well sample tap, which caused water to pool at the base of the well head. Further, the electrical conduit box at the well was not properly sealed. In March 2017, a second Citation and Compliance Order (No. 05_63_17R_001) was issued to Castro MHP for the deterioration of the well casing under the ground surface, as noted in the January 2017 inspection. This hole in the well casing has allowed shallow groundwater to enter the well and contaminate the drinking water supply for the 44 service connections in the Castro MHP. After witnessing the well failure in February 2017, DEH immediately installed a temporary connection to CWA’s potable water system as an interim measure. Since then, the Castro MHP applied for grant funding from CVWD’s Well Retrofit and Abandonment Rebate Program (funded through Proposition 84-Round 2) to seal and abandon the onsite well. The goal of the Castro MHP Water Consolidation is to provide potable water that meets or exceeds drinking water quality standards. Currently, the community is relying on a temporary highline from a CWA construction meter as the former well is no longer able to provide any water for potable or for fire protection. In order to solve this issue, there were three alternatives considered. The first alternative was to consolidate with CWA. The second alternative was to repair the existing well and the third alternative was to replace the existing well. The consolidation into CWA’s water main is the preferred alternative as it would result in more sustainable water rates for MHP residents and will increase the reliability of water service to the MHP. The primary benefit of this project is that CWA will provide Castro MHP with 32-acre feet per year (AFY) of safe, reliable potable drinking water to a DAC that can no longer rely on a deteriorated shallow groundwater well. The secondary benefit of this project is that CWA will provide the MHP with water that on average is lower in hexavalent chromium than the MHP’s well. This connection to CWA will provide Castro MHP with a 5 µg/L reduction in hexavalent chromium in drinking water to below the drinking water standard. By improving drinking water service to DACs, CWA supports these communities in avoiding environmental injustices. Consolidating SWSs with water quality issues into large water systems is typically the most cost-effective way to reduce long term water costs to these DACs. CWA has determined a useful project life of 50 years for the proposed potable water pipelines, which an industry average for water and wastewater conveyance infrastructure. Over the 50-year life of this project, 1,600 AF of clean, safe drinking water will be served to this local DAC.
2 | Project Benefits Table:
Table 3 - Project Benefits
Anticipated Useful Life of Project (years): |  |  |  |  | 50
Primary (Required)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Secondary (Optional)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Physical Benefits (At project completion or lifetime, as appropriate)
(a) |  |  | (b) |  |  |  | (c)
Benefit |  |  | Added Physical Benefit Description |  |  |  | Quantitative Benefit
Primary |  |  | Provide potable drinking water to a small system that relies on a shallow private groundwater well. |  |  |  | CWA will provide Castro MHP with 32 AFY of safe reliable potable drinking water.
Secondary |  |  | Provide potable water from CWA that meets the hexavalent chromium standard. |  |  |  | CWA will provide water that is lower in hexavalent chromium by at least 0.005 mg/L than the MHP's well
Qualitative Benefits (For Decision Support Tools, please describe non-physical benefits.)
The primary benefit is providing 32 AFY potable drinking water to Castro MHP from CWA's system through a new reliable distribution system. The secondary benefit is that the water provided to Castro MHP will be lower in hexavalent chromium, as CWA's potable water is at least 0.005 mg/L (maximum contaminant level (MCL) 0.01 mg/L) lower than Castro MHP's failed well and CWA potable water meets the MCL.
Comments: [Include narrative on additional benefits, as warranted.]
Applied water from small systems will load less arsenic and hexavalent chromium into the shallow aquifer which drains to the Salton Sea, thereby ultimately improving the water quality in the Salton Sea. These improvements in water quality will support protection of Salton Sea wetland habitat areas. By improving drinking water service to DACs, CWA supports these communities in avoiding environmental injustices. The costs to treat inorganic contaminants such as arsenic and hexavalent chromium are very high and consolidating small water systems into a larger system is usually the most cost effective method to resolve the issue long term.
* | DWR may require applicant to convert or modify Benefit Claimed and/or Benefit Units. Where applicable, select one of the following units that corresponds to the benefit claimed: • For water supply produced, saved, or recycled, enter acre-feet per year (AFY) • For water quality, enter constituent concentration reduced in mg/L • For flood damage reduction, enter inundated acres reduced in acres • For habitat improved, restored or protected, enter habitat restored in acres • For fishery benefits, enter increased fishery flow rate in cubic feet per second (cfs) • For species protection, enter number of species benefited
3 | Does the proposed project provide benefits to multiple IRWM regions [or funding areas]? If the project is located in another funding area, please provide the information requested in the 2019 Guidelines, Section 1.A.
|  | Yes | No | If yes, provide a description of the benefits to the various regions.
N/A
4 | Provide a narrative on cost considerations. For example, were other alternatives to achieve the same types and amounts of physical benefits as the proposed project evaluated? Provide a justification as to why the project was selected (e.g., if the proposed project is not the lowest cost alternative, why is it the preferred alternative? Are there any other advantages that the proposed project provides from a cost perspective?)
The cost to extend service and consolidate into the CWA should result in lower capital and operation costs to the MHP residents instead of repairing or replacing the existing well and possibly needing to install treatment to meet the arsenic or hexavalent chromium standards. Castro MHP could repair or replace the existing well; however in 2017, Riverside County DEH required the system to be highlined to CWA's system due to the poor quality of the failed well. As the system is already using CWA water it is more cost effective to consolidate the system into CWA than to repair or replace the well. Based on the system's existing technical, managerial and financial capacity and due to the age of the existing distribution system, allowing the system to continue operating on a repaired or replaced well would like result in the system having an additional failure in the future. Therefore, no formal alternatives analysis has been completed.
5 | a. Does the project address a contaminant listed in AB 1249?
|  | Yes | No | If yes, complete parts b and c:
b. Describe how the project helps address the contamination.
Yes, this project addresses hexavalent chromium contamination in a DAC water system. The project will consolidate Castro MHP, which has a well with high hexavalent chromium into CWA's water system, which meets the former MCL for hexavalent chromium.
c. Does the project provide safe drinking water to a small disadvantaged community?
|  | Yes | No | If yes, provide an explanation on how the project benefits a small disadvantaged community as defined in the 2019 IRWM Guidelines.
Yes, this project addresses hexavalent chromium and arsenic contamination in a DAC water system (45 connections) that serves less than 10,000 people and is therefore classified as a small DAC. The project will consolidate Castro MHP, which has a well with high hexavalent chromium into CWA's water system, which meets the former MCL for hexavalent chromium. The local groundwater supply of this system has shown elevated concentrations of hexavalent chromium and other constituents listed in AB 1249.
6 | Does the project provide safe, clean, affordable, and accessible water adequate for human consumption, cooking, and sanitary purposes (consistent with AB 685) to meet a specific need(s) of a community?
|  | Yes | No | If yes, please describe.
Castro MHP is a small system with its own drinking water well. The failure of the well casing has allowed shallow groundwater with hexavalent chromium to enter the well thus causing the well supply to exceed the former state standard of 0.01 mg/L. Failure of an upper well casing and intrusion of shallow groundwater can also lead to microbial contamination of a well. Consolidation of this system into CWA would provide safe, clean, affordable and accessible water to the MHP. Alternatives 2 and 3 which involve repairing or replacing the well would provide similar benefits but likely at a higher cost to residents and would not meet long term reliability requirements due to the system's technical, managerial, and financial capacity limitations.
7 | Does the project employ new or innovative technologies or practices, including decision support tools that support the integration of multiple jurisdictions, including, but not limited to, water supply, flood control, land use, and sanitation?
|  | Yes | No | If yes, please describe.
N/A
8 | If the project provides benefits (75% by population or geography) to a DAC, explain the need of the DAC and how the project will address the described need. Explain how the area/community meets the definition of a DAC.
Castro MHP is classified as 100% DAC by geography with a median household incomes less than 60 percent of the California statewide MHI, and depends on its own supply well to supply their drinking water. Creating drinking water reliability for the Castro MHP is critical to ensuring public health. The water system is currently operated by the system owners. Consolidating the mobile home park into the CWA potable water system would provide a higher level of security, reliability and redundancy as the CWA system is operated and maintained by full-time State of California certified operational staff. Additionally, the existing fire suppression system for the mobile home park offers less protection than a municipal water supply could provide. Therefore, consolidation into the CWA system would provide a more robust and reliable means for fire protection.
9 | If the project provides benefits (75% by population or geography) to an EDA, explain the need of the EDA and how the project will address the described need. Explain how the area/community meets the definition of an EDA.
N/A
10 | If the project provides benefits (75% by population or geography) to a Tribe or a Tribe is the sponsor of the project, explain the need of the Tribe and how the project will address the described need.
N/A
11 | Does the project sponsor have legal access rights, easements, or other access capabilities to the property to implement the project?
|  | Yes | If yes, please describe.
|  | NA | If NA, please describe why physical access to a property is not needed.
|  | No | If no, please provide a clear and concise narrative with a schedule to obtain necessary access.
Part of the construction will occur in the public right-of way and the City of Coachella has waived the fees for the encroachment permit to install the piping and complete the pavement repairs. The MHP is privately owned and as part of the consolidation agreement, CWA will have legal access and easements to install the mainline in any MHP owned streets and service meters, service connections and fire hydrants on MHP owned parcels.
E. | ENVIRONMENTAL
1 | Please fill out the CEQA Timeline Table below, if applicable:
Table 4 - CEQA Timeline
CEQA STEP |  |  |  |  | COMPLETE? (y/n) |  |  | ESTIMATED DATE TO COMPLETE
|  | Initial Study |  |  | Y |  |  | 2019-09-30
|  | Notice of Preparation |  |  | N |  |  | NA
|  | Draft EIR/MND/ND |  |  | N |  |  | NA
|  | Public Review |  |  | N |  |  | NA
|  | Final EIR/MND/ND |  |  | N |  |  | NA
|  | Adoption of Final EIR/MND/ND |  |  | N |  |  | NA
|  | Notice of Determination |  |  | N |  |  | 2020-05-31
a. If additional explanation or justification of the timeline is needed, please describe below (optional).
Initial Study, including biological and cultural reports, was completed in September 2019. A Notice of Exemption will be completed for the project by December 31, 2019. After grant award in April 2020, a Notice of Determination will be filed with the State Clearinghouse and Riverside County clerk.
2 | Permit Acquisition Plan:
List all permits needed to complete the project. If the project does not provide benefits to a DAC, EDA, or Tribe (min 75%), all permits needed to begin construction must be acquired within 12 months of Final Award.
No. |  | Type of Permit |  |  | Permitting Agency |  |  | Date Acquired or Anticipated
1 |  | Encroachment, Road & Construction |  |  | City of Coachella |  |  | Waived
2 |  | Permit to Construct |  |  | SCAQMD |  |  | 2020-06-01
3 |  | Fugitive Dust Control Plan |  |  | SCAQMD |  |  | 2020-06-01
4 |  | General Permit for Stormwater Discharge |  |  | SWRCB |  |  | 2020-06-01
5 |  | General Permit for Constr. Discharges |  |  | RWQCB, Colorado River |  |  | 2020-06-01
6
n.
For each permit not yet acquired, describe the following:
No. |  | a. Actions taken to date (include dates of any key meetings, consultations, submittals, etc.) |  |  |  | b. Any issues or obstacles that may delay acquisition of permit
1
2
3
4
5
n.
3 | Permitting Checklist: This checklist is provided as a courtesy for documentation purposes. Not all permits which may apply are listed. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
a. | Does the project involve any activities that may affect federally or state listed threatened or endangered species or their critical habitat that are known, or have a potential, to occur on-site, in the surrounding area, or in the service area? (i.e. Federal Endangered Species Act Section 7 Consultation and Incidental Take Authorization and Section 10 Incidental Take Permit, California Endangered Species Act Permit, and/or ESA & CESA Consistency Determination)
|  | Yes | No | If yes, please explain:
N/A
b. | Would the proposed project work in, over, or under navigable waters of the US or discharge dredged or fill material in waters of the US? (i.e. Rivers & Harbors Act Section 10 Permit and/or Clean Water Act Section 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
c. | Will the proposed project have the potential to affect historical, archaeological, or cultural resources? (i.e. National Historic Preservation Act and/or State Historic Preservation Officer Consultation)
|  | Yes | No | If yes, please explain:
N/A
d. | Will the proposed project discharge into a water of the US? (i.e. Clean Water Act Section 401 and/or 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
e. | Will the proposed project divert the natural flow of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
f. | Will the proposed project change the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
g. | Will the proposed project use any material from the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
h. | Will the proposed project deposit or dispose of debris, waste, or other material containing crumbled, flaked, or ground pavement where it can pass into a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement/National Pollutant Discharge Elimination System Permit/Waste Discharge Requirements Permit)
|  | Yes | No | If yes, please explain:
N/A
i. | For water supply projects, do you need to obtain a water right? (Water Rights Permit)
|  | Yes | No | If yes, please explain:
N/A
j. | Is the proposed project within the defined coastal zone? (Coastal Development Permit)
|  | Yes | No | If yes, please explain:
N/A

## Answers (hidden)
A. PROJECT INFORMATION
1
2
3
4
5
6
7
8
9

## List Values (hidden)
Eligible Applicant Type | IRWM Regions | Project Type | Benefit Claimed | Benefit Units | Statewide Priorities
| American River Basin |  |  |  | 1. Make Conservation a California Way of Life
Public Agency | Antelope Valley | Conjunctive use | Ecosystem Restoration | acre(s) | 2. Increase Regional Self-Reliance and Integrated Water Management Across All Levels of Government
Non-profit Organization | Anza Borrego Desert | Decision support tool | Ecosystem/Freshwater habitat | AFY | 3. Achieve the Co-Equal Goals for the Delta
Public Utility | Coachella Valley | Groundwater aquifer cleanup | Fishery Improvements | cfs | 4. Protect and Restore Important Ecosystems
Federally Recognized Indian Tribe | Cosumnes, American, Bear, Yuba (CABY) | Other | Flood Damage Reduction | mg/L | 5. Manage and Prepare for Dry Periods
Indian Tribe listed on the Native American Heritage Commission’s California Tribal Consultation List | East Contra Costa County | Recharge project | Flood Management | Other | 6. Expand Water Storage Capacity and Improve Groundwater Management
Mutual Water Company | East Stanislaus | Stormwater management | Groundwater Recharge |  | 7. Provide Safe Water for All Communities
| Eastern San Joaquin | Surface storage | Habitat Restoration |  | 8. Increase Flood Protection
| Fremont Basin | Underground water storage | Operational Efficiency |  | 9. Increase Operational and Regulatory Efficiency
| Greater Los Angeles County | Water conservation | Grant Admin |  | 10. Identify Sustainable and Integrated Financing Opportunities
| Greater Monterey County | Water conveyance facility | Reduce Groundwater Pumping |  |  | ListBox Option
| Imperial | Water desalination | Flood Protection
| Inyo-Mono | Water quality | Stormwater Management
| Kaweah River Basin | Water recycling | Streamflow Restoration
| Kern County | Water reuse | Water Conservation
| Kings Basin Water Authority | Watershed project | Water Quality
| Lahontan Basins | Water-use efficiency | Water Quality - Groundwater
| Madera |  | Water Quality - Sediment
| Merced |  | Water Quality - Surface Water
| Mojave |  | Water Supply - Groundwater
| Mokelumne/Amador/Calaveras (MAC) |  | Water Supply - Recycled Water
| Monterey Peninsula, Carmel Bay, So. Monterey Bay |  | Water Supply - Surface Water
| North Coast |  | Water Supply Reliability
| North Sacramento Valley |  | Other
Pajaro River Watershed
Poso Creek
San Diego
San Francisco Bay Area
San Gorgonio
San Luis Obispo
Santa Ana River Watershed
Santa Barbara County
Santa Cruz County
South Orange County Watershed Management Area
Southern Sierra
Tahoe-Sierra
Tule River Basin
Tuolumne-Stanislaus
Upper Feather River Watershed
Upper Pit River Watershed
Upper Sacramento-McCloud
Upper Santa Clara River
Upper Santa Margarita
Watersheds Coalition of Ventura County
Westside (Yolo, Solano, Napa, Lake, Colusa)
Westside-San Joaquin
Yosemite-Mariposa
Yuba County