## PIF
A. | PROJECT INFORMATION
1 | Project Title: |  |  | East Coachella Valley Water Supply Project - Avenue 66 Phase 2B
2 | Project Sponsor(s): |  |  | Coachella Valley Water District
3 | Eligible Applicant Type:
4 | IRWM Project Region(s): |  |  | Coachella Valley Regional Water Management Group
5 | Does the project provide benefits directly to a Disadvantaged Communities (DAC) and/or Economically Distressed Areas (EDA) (minimum 75% by population or geography)?
|  | Yes | No | If yes, please complete D.8 and/or D.9. Show on map if applicable.
6 | Is the Project Sponsor a Tribe, or does the project provide benefits to a Tribe (minimum 75% by population or geography) as defined by Proposition 1?
|  | Yes | No | If yes, please complete D.10. Show on map if applicable.
7 | Provide project map. Include location of project, project benefit and/or service area, and other applicable information.
8. Funding Category:
DAC Implementation Project
General Implementation Project
9. Project Type: | [5 empty] | Other: | water consolidation
Select most applicable project type. See Section II.C. of the 2019 Guidelines for full description of eligible project types. If "Other" is selected, please write in the space provided the proposed project type.
B. | SELECTED ELIGIBILITY REQUIREMENTS
1 | Will the project be included in the IRWM Plan, that will be adopted prior to anticipated Agreement Execution?
|  | Yes | No
2 | Does the project address a critical need(s) and/or priority(ies) of the IRWM Region as identified in the IRWM Plan?
|  | Yes | No | If yes, complete part a:
a. | What IRWM Plan goal(s)/objective(s) does the project address? Identify and explain.
Objective A: Provide reliable water supply. This project will provide a reliable and safe water supply for a small DAC water system with impaired water quality to CVWD's potable water system. Providing safe reliable drinking water to local DACs is a goal of multiple stakeholders. Objective B: Manage groundwater levels. The project will reduce the amount of groundwater pumped in the basin to manage groundwater levels and reduce overdraft by converting small water systems that rely on contaminated groundwater to CVWD's potable water system, the Manuela Garcia MHP would no longer be pumping from the shallow groundwater. Objective K: Address water-related needs of local Native American culture. This project will address water-related needs of the Torres-Martinez Desert Cahuilla Indians because the Manuela Garcia MHP is located on their reservation lands. Objective L: Address water and sanitation needs of DACs. This project will provide a reliable, safe water supply by consolidating an individual SWS with impaired water quality in a DAC to CVWD’s potable water supply. Objective M: Maintain affordability of water. This project helps to maintain the affordability of water because users will receive a monthly bill with consistent rates. Objective E and J are also met - see Attachment 4 Work Plan.
3 | Does the project have an expected useful life consistent with Government Code §16727 (generally 15 years)? If not, explain why this requirement is not applicable.
The infrastructure constructed will become part of CVWD's potable water system and will be operated and maintained in perpetuity. The anticipated life cycle of the pipeline and its appurtenances is projected to be well over 50 years, based on historical data provided by several pipeline manufacturers and studies.
4 | Does the project address and/or adapt to the effects of climate change? Does the project address the climate change vulnerabilities assessed in the IRWM Plan?
|  | Yes | No | If yes, please explain below.
In Chapter 3 of the 2018 Coachella Valley IRWM/SWR Plan Update, the Region created models to project climate change impacts to water supplies and infrastructure. Generally, climate change is expected to increase temperatures, with little to no change in average rainfall, and increase in water demand due to higher irrigation needs caused by increased temperatures. This project directly addresses medium priority vulnerabilities related to “Water Demand: Limited ability to meet summer demand” by improving access to safe drinking water and abandoning inefficient small system wells that depend on recharge water. Local conveyance is a “no regret” strategy that helps to both adapt to climate change and mitigate GHG emissions. By consolidating small systems into larger water systems, it provides local residents with clean, safe, affordable and reliable drinking water that they typically would not be able to obtain. As more small systems get consolidated into the larger systems, water loss and groundwater contamination associated with poorly maintained wells will be reduced. This project allows the Region to better regulate water usage by reducing the number of extraction points throughout the basin. The consolidation of these smaller systems will help better manage the basin’s water supply.
5 | Does the project contribute to regional water self-reliance?
|  | Yes | No | If yes, please explain below.
The Avenue 66 Phase 2B Project proposes a pipeline along Avenue 66 connecting to the existing CVWD potable system, providing redundancy within the system, improving the water reliability. The project will expand the region’s domestic water systems to deliver safe drinking water to a DAC, which reduces the number of pumpers in the groundwater basin and protects this and other DACs from continued degradation of the shallow aquifer associated with climate changes – thereby improving the region's water supply reliability and self-reliance (a healthy groundwater basin).
6 | Does the project provide a benefit that meets at least one of the Statewide Priorities as defined in the 2019 IRWM Grant Program Guidelines?
|  | Yes | No | If yes, please identify below.
7 | Will CEQA be completed within 12 months of Final Award?
Yes
NA, project is exempt under CEQA
NA, not a project under CEQA
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
8 | Will all permits necessary to begin construction be acquired within 12 months of Final Award?
Yes
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
C. | WORK PLAN, BUDGET, and SCHEDULE SUMMARY
1 | Project Description: Provide a brief project description summarizing major components, objectives, goals, and intended outcomes/benefits (quantitative and qualitative).
The ECVWSP - Ave 66 Phase 2B Project consists of the pipeline that would connect the Manuela Garcia MHP to the existing 24-inch CVWD pipeline at the intersection of Avenue 66 and Polk Street. The Manuela Garcia MHP is a Riverside County Department of Environmental Health (DEH) permitted SWS that serves a mobile home park with a total of 14 service connections. The small water system is reliant on an 8-inch diameter groundwater well that is 500 feet (ft) deep. The well has a submersible pump that delivers water to six pressure tanks to supply the potable water distribution system. There is also a second well with a 510 ft deep, 6-inch casing. This well was originally used for potable water but has since been repurposed for irrigation and is no longer connected to the potable water system. The existing potable water distribution system consists of 2-inch schedule 40 PVC pipelines. In 2013, the Manuela Garcia MHP SWS installed under the counter reverse osmosis (RO) treatment units for each mobile home to remove arsenic which was present at concentrations exceeding the regulatory maximum contaminant limit (MCL) of 0.010 mg/L. A separate fire suppression system consists of 4-inch PVC piping and two fire hydrants. The fire suppression system is gravity fed from three 5,000-gallon storage tanks. The fire suppression system is separated from the potable water distribution system via an air gap between the supply line and the tanks. The Avenue 66 Phase 2B project will be 7,250 linear feet of 30-inch diameter ductile iron potable water pipeline from the connection at the Manuela Garcia MHP to the existing CVWD water system at the intersection of Avenue 66 and Polk Street to the west. The Avenue 66 Phase 2B pipeline is required to consolidate Manuela Garcia MHP.
2 | Budget: Provide cost estimates for each Budget Category listed in the table below. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 1 - Project Budget
Category |  |  | (a) |  | (b) |  | (c) | (c) | (d)
|  |  | Cost Share: Non‐ State Fund Source |  | Requested Grant Amount |  | Other Cost Share (including other State Sources) |  | Total Cost
(a) | Project Administration |  | 16000 |  | 18750 |  | 0 |  | 34750
(b) | Land Purchase/ Easement |  | 42200 |  | 0 |  | 0 |  | 42200
(c) | Planning/Design /Engineering /Environmental Documentation |  | 444000 |  | 0 |  | 0 |  | 444000
(d) | Construction/ Implementation |  | 3332040 |  | 1250000 |  | 1800000 |  | 6382040
(e) | Grand Total (Sum rows (a) through (d) for each column) |  | 3834240 |  | 1268750 |  | 1800000 |  | 6902990
Note: Provide information or other documentation to support the cost estimate in a separate attachment. Identify the source of all cost share and other funds. If other funds are not used, describe efforts to obtain other funding and/or why other funding sources were not used.
The non-state funding match will be provided by CVWD’s CIP. Other cost share will be paid for by a SWRCB Drinking Water SRF loan. Application is currently underway by CVWD.
3 | Cost Share Waiver Requested (DAC or EDA)? |  |  |  |  | Yes | No | If yes, continue below:
Cost Share Waiver Justification: Describe what percentage of the proposed project area encompasses a DAC/EDA, how the community meets the definition of a DAC/EDA, and the need of the DAC/EDA that the project addresses. In order to receive a cost share waiver, the applicant must demonstrate that the project will provide benefits (minimum 25% by population or geography) that address a need of a DAC and/or EDA.
The Avenue 66 Phase 2B Project is located immediately adjacent to the west of the unincorporated community of Mecca in Riverside County, California. The Avenue 66 Phase 2B Project would connect Manuela Garcia Mobile Home Park (MHP), a 100% severely DAC located on tribal land, into the CVWD water system. Manuela Garcia MHP is located in a block group that has a MHI of $22,156 per the DWR Mapping Tool. Creating drinking water reliability for the identified system is critical to ensuring public health within the mobile home park. Based on the Riverside County DEH Inspection Reports, the Manuela Garcia MHP has shown MCL exceedances for arsenic in its groundwater supply well.
4 | Schedule: Include reasonable estimates of the start and end dates for each Budget Category listed in Table 1 - Project Budget. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 2 - Project Schedule
Category |  |  |  |  | (a) Start Date |  |  | (b) End Date
(a) | Direct Project Administration |  |  |  | 2020-04-15 |  |  | 2024-04-30
(b) | Land Purchase/ Easement |  |  |  | 2020-04-15 |  |  | 2020-12-22
(c) | Planning/Design/Engineering/Environmental Documentation |  |  |  | 2020-04-15 |  |  | 2022-09-12
(d) | Construction/ Implementation |  |  |  | 2022-11-01 |  |  | 2024-01-31
D. | OTHER PROJECT INFORMATION
1 | Provide a narrative for project justification. If applicable, include references to supporting documentation such as models, studies, engineering reports, etc. Include any other information that supports the justification for this project, including how the project can achieve the claimed level of benefits.
In the eastern Coachella Valley, there are a number of rural communities that are not connected to CVWD's potable water system. These communities are classified as DACs and depend on local private wells connected to independent small water systems to supply their drinking water. The local groundwater supply of Manuel Garcia MHP has shown elevated concentrations of arsenic and other constituents that are currently regulated by the State or may be in the near future (e.g. hexavalent chromium). In order to improve the reliability and potential safety of water supply to the small water systems in the eastern Coachella Valley, CVWD evaluated consolidation of the several small water systems into CVWD's potable water system in two Technical Memorandums (TM) dated June and October 2018 (East Coachella Valley Water Supply Project (ECVWSP) - System Identification TM and ECVWSP - System Prioritization TM). CVWD evaluated and prioritized 83 small systems for consolidation. CVWD is partnering with its DAC Infrastructure Task Force to implement the prioritized projects in coordination with other water and wastewater infrastructure projects in the eastern Coachella Valley. Based on the criteria and weights determined from discussions with CVWD, one of the highest priority projects is the Avenue 66 Phase 2B Project, which is a component of the Saint Anthony MHP Water Consolidation Project (Saint Anthony Project). A preliminary engineering report and environmental compliance documentation has been completed for the Avenue 66 Phase 2B Project in May 2019 and September 2019, respectively (ECVWSP Saint Anthony MHP Consolidation Project Prelminary Engineering Report and ECVWSP Saint Anthony MHP Consolidation Project Final Initial Study/Mitigated Negative Declaration). The Avenue 66 Phase 2B Project proposes to consolidate Manuela Garcia MHP, which has 14 service connections. Based on the system's average day demand of 7.6 gallons per minute, the project will provide 13 acre feet per year of safe reliable drinking water to MHP residents.
2 | Project Benefits Table:
Table 3 - Project Benefits
Anticipated Useful Life of Project (years): |  |  |  |  | 50
Primary (Required)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Secondary (Optional)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Physical Benefits (At project completion or lifetime, as appropriate)
(a) |  |  | (b) |  |  |  | (c)
Benefit |  |  | Added Physical Benefit Description |  |  |  | Quantitative Benefit
Primary |  |  | Provide potable drinking water to small systems that rely on shallow private groundwater wells. |  |  |  | 13 afy of clean, safe potable drinking water to a small water system
Secondary |  |  | Provide potable water from CVWD that averages non-detect in arsenic concentrations. |  |  |  | Arsenic concentration reduced by 24 ug/L.
Qualitative Benefits (For Decision Support Tools, please describe non-physical benefits.)
Comments: [Include narrative on additional benefits, as warranted.]
The primary benefit of this project is that it will provide 13 AFY (7.6 gallons per minute (gpm) Average Day Demand) of clean, safe, affordable and accessible water for human consumption, cooking and sanitary purposes, per Assembly Bill 685 (Human Right to Water) to Manuela Garcia MHP. The current system relies on shallow, degraded groundwater wells. Consolidating SWSs with water quality issues into large water systems is typically the most cost-effective way to reduce long term water costs to these DACs. CVWD has determined a useful project life of 50 years for the proposed potable water pipelines, which an industry average for water and wastewater conveyance infrastructure. Over the 50-year life of this project, 650 AF of clean, safe drinking water will be served to this local DAC on Torres-Martinez Band of Desert Cahuilla Indians tribal lands. The secondary benefit is that this project will reduce the arsenic concentration in their drinking water by 24 (ug/L. CVWD potable water averages non-detect level of arsenic. The applied water from small systems will load less arsenic into the shallow groundwater aquifer, which drains to the Salton Sea, thereby ultimately improving the water quality in the Salton Sea. These improvements in water quality will support protection of the Salton Sea wetland habitat areas.
* | DWR may require applicant to convert or modify Benefit Claimed and/or Benefit Units. Where applicable, select one of the following units that corresponds to the benefit claimed: • For water supply produced, saved, or recycled, enter acre-feet per year (AFY) • For water quality, enter constituent concentration reduced in mg/L • For flood damage reduction, enter inundated acres reduced in acres • For habitat improved, restored or protected, enter habitat restored in acres • For fishery benefits, enter increased fishery flow rate in cubic feet per second (cfs) • For species protection, enter number of species benefited
3 | Does the proposed project provide benefits to multiple IRWM regions [or funding areas]? If the project is located in another funding area, please provide the information requested in the 2019 Guidelines, Section 1.A.
|  | Yes | No | If yes, provide a description of the benefits to the various regions.
4 | Provide a narrative on cost considerations. For example, were other alternatives to achieve the same types and amounts of physical benefits as the proposed project evaluated? Provide a justification as to why the project was selected (e.g., if the proposed project is not the lowest cost alternative, why is it the preferred alternative? Are there any other advantages that the proposed project provides from a cost perspective?)
The June and October 2018 Technical Memorandums evaluated consolidation of 83 identified small water systems in the eastern Coachella Valley. The planning level cost of consolidation all identified systems was $71,974,000. This alternative is not feasible due to the high estimated capital and annualized costs required to consolidate all identified SWS projects. The estimated total capital cost is beyond the ability for CVWD to apply for and secure outside funding since non-ratepayer funds are required to pay for the consolidation projects. The Avenue 66 Phase 2B project which serves Manuela Garcia MHP and is part of the larger Saint Anthony Project) was selected since this alternative allows CVWD to address one of the small water systems with the most pressing water quality and health concern needs. Alternatively, the system would be required to maintain their well, under the counter RO units to treat arsenic, and existing well with water rate revenue from a customer base of only 14 connections. Consolidating into the larger CVWD system provides a larger cost base to cover the costs of water supply, treatment and distribution. A cost analysis was included in the May 2019 Preliminary Engineering Report.
5 | a. Does the project address a contaminant listed in AB 1249?
|  | Yes | No | If yes, complete parts b and c:
b. Describe how the project helps address the contamination.
Yes, this project addresses arsenic contamination in a DAC water system. The project will consolidate Manuela Garcia MHP, which has a well with high arsenic into CVWD's water system, which meets the drinking water standard for arsenic.
c. Does the project provide safe drinking water to a small disadvantaged community?
|  | Yes | No | If yes, provide an explanation on how the project benefits a small disadvantaged community as defined in the 2019 IRWM Guidelines.
Yes, this project addresses arsenic contamination in a DAC water system (14 connections) that serves less than 10,000 people and is therefore classified as a small DAC. The project will consolidate Manuela Garcia MHP, which has a well with high arsenic into CVWD's water system, which meets the drinking water standard for arsenic. The local groundwater supply of this system has shown elevated concentrations of hexavalent chromium and other constituents listed in AB 1249.
6 | Does the project provide safe, clean, affordable, and accessible water adequate for human consumption, cooking, and sanitary purposes (consistent with AB 685) to meet a specific need(s) of a community?
|  | Yes | No | If yes, please describe.
The primary benefit of this project is that it will provide 13 AFY (7.6 gallons per minute (gpm) Average Day Demand) of clean, safe, affordable and accessible water for human consumption, cooking and sanitary purposes, per Assembly Bill 685 (Human Right to Water) to Manuela Garcia MHP. The current system relies on shallow, degraded groundwater wells. By improving drinking water service to DACs, CVWD supports these communities in avoiding environmental injustices. Consolidating SWSs with water quality issues into large water systems is typically the most cost-effective way to reduce long term water costs to these DACs.
7 | Does the project employ new or innovative technologies or practices, including decision support tools that support the integration of multiple jurisdictions, including, but not limited to, water supply, flood control, land use, and sanitation?
|  | Yes | No | If yes, please describe.
N/A
8 | If the project provides benefits (75% by population or geography) to a DAC, explain the need of the DAC and how the project will address the described need. Explain how the area/community meets the definition of a DAC.
This project is not requesting a cost share waiver. However, the project would consolidate Manuela Garcia MHP, a 100% DAC system located on tribal land into the CVWD domestic water system. The project will directly improve water quality and supply reliabilty for the DAC and address contamination per the requirements of AB 1249 by providing water that meets the arsenic drinking water standard. Manuela Garcia is located in a Block Group per the DWR Mapping Tool that has a MHI of $22,156. A severely DAC system has a MHI of 60% of the statewide MHI or $38,272.
9 | If the project provides benefits (75% by population or geography) to an EDA, explain the need of the EDA and how the project will address the described need. Explain how the area/community meets the definition of an EDA.
N/A
10 | If the project provides benefits (75% by population or geography) to a Tribe or a Tribe is the sponsor of the project, explain the need of the Tribe and how the project will address the described need.
The project will connect the Manuela Garcia MHP which is located 100% on Torres-Martinez Desert Cahuilla Indians' tribal lands. The project would consolidate Manuela Garcia MHP, a 100% DAC system into the CVWD domestic water system. The project will directly improve water quality and supply reliabilty for the DAC and address contamination per the requirements of AB 1249 by providing water that meets the arsenic drinking water standard. The project will also provides a 30-inch diameter CVWD domestic water line along 7,250 feet of the border of Torres-Martinez lands, which will allow other tribal properties to connect to CVWD potable water in lieu of relying on contaminated groundwater.
11 | Does the project sponsor have legal access rights, easements, or other access capabilities to the property to implement the project?
|  | Yes | If yes, please describe.
|  | NA | If NA, please describe why physical access to a property is not needed.
|  | No | If no, please provide a clear and concise narrative with a schedule to obtain necessary access.
Most facilities would be constructed within public right-of-way of established roadways and would only require an Encroachment Permit from the County of Riverside. Easement acquisition is anticipated for up to 4 privately owned parcels directly adjacent to the north boundary line of Avenue 66 from Polk Street to the Manuela Garcia MHP. A licensed surveyor will prepare legal descriptions and exhibits for acquiring easements, some of which will be on the Torrez-Martinez Reservation. Land Title status will be determined by records in the Land Title and Records Office in consultation with the Riverside office of the Bureau of Indian Affairs (BIA). Once Tribal approval is received, CVWD’s consultant will prepare the necessary appraisals and application to the BIA for a formal easement. Once all easements have been acquired, the land agent will prepare a certification of right of way for the project. This will begin upon grant award and is estimated to be complete by December 2020.
E. | ENVIRONMENTAL
1 | Please fill out the CEQA Timeline Table below, if applicable:
Table 4 - CEQA Timeline
CEQA STEP |  |  |  |  | COMPLETE? (y/n) |  |  | ESTIMATED DATE TO COMPLETE
|  | Initial Study |  |  | Y |  |  | 2019-07-24
|  | Notice of Preparation |  |  | N |  |  | N/A
|  | Draft EIR/MND/ND |  |  | N |  |  | 2019-07-24
|  | Public Review |  |  | N |  |  | 7/25/2019 to 8/23/2019
|  | Final EIR/MND/ND |  |  | N |  |  | 2019-09-01
|  | Adoption of Final EIR/MND/ND |  |  | N |  |  | 2019-09-01
|  | Notice of Determination |  |  | N |  |  | 2019-09-01
a. If additional explanation or justification of the timeline is needed, please describe below (optional).
Public Review Draft IS/MND for the Saint Anthony MHP Water Consolidation Project was issued on July 24, 2019 and has a public comment period open from July 25 to August 23, 2019.
2 | Permit Acquisition Plan:
List all permits needed to complete the project. If the project does not provide benefits to a DAC, EDA, or Tribe (min 75%), all permits needed to begin construction must be acquired within 12 months of Final Award.
No. |  | Type of Permit |  |  | Permitting Agency |  |  | Date Acquired or Anticipated
1 |  | Encroachment, Road and Construction Permits |  |  | County of Riverside |  |  | 2022-09-12
2 |  | Permit to Construct |  |  | South Coast Air Quality Management |  |  | 2022-09-12
3 |  | Fugutive Dust Control Plan |  |  | South Coast Air Quality Management |  |  | 2022-09-12
4 |  | NPDES General Permit for Stormwater Discharges |  |  | SWRCB |  |  | 2022-09-12
5 |  | General Permit for Construction Discharges |  |  | RWQCB, Colorado River |  |  | 2022-09-12
6
7
8
9
For each permit not yet acquired, describe the following:
No. |  | a. Actions taken to date (include dates of any key meetings, consultations, submittals, etc.) |  |  |  | b. Any issues or obstacles that may delay acquisition of permit
1
2
3
4
5
n.
3 | Permitting Checklist: This checklist is provided as a courtesy for documentation purposes. Not all permits which may apply are listed. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
a. | Does the project involve any activities that may affect federally or state listed threatened or endangered species or their critical habitat that are known, or have a potential, to occur on-site, in the surrounding area, or in the service area? (i.e. Federal Endangered Species Act Section 7 Consultation and Incidental Take Authorization and Section 10 Incidental Take Permit, California Endangered Species Act Permit, and/or ESA & CESA Consistency Determination)
|  | Yes | No | If yes, please explain:
N/A
b. | Would the proposed project work in, over, or under navigable waters of the US or discharge dredged or fill material in waters of the US? (i.e. Rivers & Harbors Act Section 10 Permit and/or Clean Water Act Section 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
c. | Will the proposed project have the potential to affect historical, archaeological, or cultural resources? (i.e. National Historic Preservation Act and/or State Historic Preservation Officer Consultation)
|  | Yes | No | If yes, please explain:
N/A
d. | Will the proposed project discharge into a water of the US? (i.e. Clean Water Act Section 401 and/or 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
e. | Will the proposed project divert the natural flow of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
f. | Will the proposed project change the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
g. | Will the proposed project use any material from the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
h. | Will the proposed project deposit or dispose of debris, waste, or other material containing crumbled, flaked, or ground pavement where it can pass into a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement/National Pollutant Discharge Elimination System Permit/Waste Discharge Requirements Permit)
|  | Yes | No | If yes, please explain:
N/A
i. | For water supply projects, do you need to obtain a water right? (Water Rights Permit)
|  | Yes | No | If yes, please explain:
N/A
j. | Is the proposed project within the defined coastal zone? (Coastal Development Permit)
|  | Yes | No | If yes, please explain:
N/A

## Answers (hidden)
A. PROJECT INFORMATION
1
2
3
4
5
6
7
8
9

## List Values (hidden)
Eligible Applicant Type | IRWM Regions | Project Type | Benefit Claimed | Benefit Units | Statewide Priorities
| American River Basin |  |  |  | 1. Make Conservation a California Way of Life
Public Agency | Antelope Valley | Conjunctive use | Ecosystem Restoration | acre(s) | 2. Increase Regional Self-Reliance and Integrated Water Management Across All Levels of Government
Non-profit Organization | Anza Borrego Desert | Decision support tool | Ecosystem/Freshwater habitat | AFY | 3. Achieve the Co-Equal Goals for the Delta
Public Utility | Coachella Valley | Groundwater aquifer cleanup | Fishery Improvements | cfs | 4. Protect and Restore Important Ecosystems
Federally Recognized Indian Tribe | Cosumnes, American, Bear, Yuba (CABY) | Other | Flood Damage Reduction | mg/L | 5. Manage and Prepare for Dry Periods
Indian Tribe listed on the Native American Heritage Commission’s California Tribal Consultation List | East Contra Costa County | Recharge project | Flood Management | Other | 6. Expand Water Storage Capacity and Improve Groundwater Management
Mutual Water Company | East Stanislaus | Stormwater management | Groundwater Recharge |  | 7. Provide Safe Water for All Communities
| Eastern San Joaquin | Surface storage | Habitat Restoration |  | 8. Increase Flood Protection
| Fremont Basin | Underground water storage | Operational Efficiency |  | 9. Increase Operational and Regulatory Efficiency
| Greater Los Angeles County | Water conservation | Grant Admin |  | 10. Identify Sustainable and Integrated Financing Opportunities
| Greater Monterey County | Water conveyance facility | Reduce Groundwater Pumping |  |  | ListBox Option
| Imperial | Water desalination | Flood Protection
| Inyo-Mono | Water quality | Stormwater Management
| Kaweah River Basin | Water recycling | Streamflow Restoration
| Kern County | Water reuse | Water Conservation
| Kings Basin Water Authority | Watershed project | Water Quality
| Lahontan Basins | Water-use efficiency | Water Quality - Groundwater
| Madera |  | Water Quality - Sediment
| Merced |  | Water Quality - Surface Water
| Mojave |  | Water Supply - Groundwater
| Mokelumne/Amador/Calaveras (MAC) |  | Water Supply - Recycled Water
| Monterey Peninsula, Carmel Bay, So. Monterey Bay |  | Water Supply - Surface Water
| North Coast |  | Water Supply Reliability
| North Sacramento Valley |  | Other
Pajaro River Watershed
Poso Creek
San Diego
San Francisco Bay Area
San Gorgonio
San Luis Obispo
Santa Ana River Watershed
Santa Barbara County
Santa Cruz County
South Orange County Watershed Management Area
Southern Sierra
Tahoe-Sierra
Tule River Basin
Tuolumne-Stanislaus
Upper Feather River Watershed
Upper Pit River Watershed
Upper Sacramento-McCloud
Upper Santa Clara River
Upper Santa Margarita
Watersheds Coalition of Ventura County
Westside (Yolo, Solano, Napa, Lake, Colusa)
Westside-San Joaquin
Yosemite-Mariposa
Yuba County