## PIF
A. | PROJECT INFORMATION
1 | Project Title: |  |  | East Coachella Valley Septic to Sewer Conversion - Monroe Street
2 | Project Sponsor(s): |  |  | Coachella Valley Water District
3 | Eligible Applicant Type:
4 | IRWM Project Region(s): |  |  | Coachella Valley Regional Water Management Group
5 | Does the project provide benefits directly to a Disadvantaged Communities (DAC) and/or Economically Distressed Areas (EDA) (minimum 75% by population or geography)?
|  | Yes | No | If yes, please complete D.8 and/or D.9. Show on map if applicable.
6 | Is the Project Sponsor a Tribe, or does the project provide benefits to a Tribe (minimum 75% by population or geography) as defined by Proposition 1?
|  | Yes | No | If yes, please complete D.10. Show on map if applicable.
7 | Provide project map. Include location of project, project benefit and/or service area, and other applicable information.
8. Funding Category:
DAC Implementation Project
General Implementation Project
9. Project Type: | [5 empty] | Other: | Wastewater Consolidation
Select most applicable project type. See Section II.C. of the 2019 Guidelines for full description of eligible project types. If "Other" is selected, please write in the space provided the proposed project type.
B. | SELECTED ELIGIBILITY REQUIREMENTS
1 | Will the project be included in the IRWM Plan, that will be adopted prior to anticipated Agreement Execution?
|  | Yes | No
2 | Does the project address a critical need(s) and/or priority(ies) of the IRWM Region as identified in the IRWM Plan?
|  | Yes | No | If yes, complete part a:
a. | What IRWM Plan goal(s)/objective(s) does the project address? Identify and explain.
Objective E: Preserve groundwater quality. This project involves removing septic tanks from the perched groundwater which flows to the local agricultural drainage system and the Salton Sea. The perched aquifer has documented high nitrate levels that are contributed from leaching septic tanks. Objective K: Address water related needs of local Native American culture. The project connects a community on the Torres Martinez Desert Cahuilla Indians Reservation to CVWD’s sanitary sewer system. Objective L: Address water and sanitation needs of disadvantaged communities. The project addresses the sanitation needs of the Torres Martinez Desert Cahuilla Indians, the reservation lands lie within a designated DAC, see project map. The project will also prevent the Tribe’s drinking water wells from being impacted by bacteria and/or N discharges from the failing sewage systems. Objective M: Maintain affordability of water. The project would help maintain the affordability of water by providing MHP residents with a known monthly cost for sewer as opposed to burdening them with the unpredictable costs associated with failing septic systems. This project also meets Objectives F and J - see Attachment 4 Work Plan.
3 | Does the project have an expected useful life consistent with Government Code §16727 (generally 15 years)? If not, explain why this requirement is not applicable.
The proposed Project will expand a municipal wastewater collection system. The collection system components (i.e. VCP pipeline, PCC manholes, etc.) have an expected service life of 50 years; and with routine maintenance, can last even longer. When constructed, these facilities will become a permanent part of CVWD's sewer system and will be operated and maintained in perpetuity.
4 | Does the project address and/or adapt to the effects of climate change? Does the project address the climate change vulnerabilities assessed in the IRWM Plan?
|  | Yes | No | If yes, please explain below.
In Chapter 3 of the 2018 Coachella Valley IRWM/SWR Plan Update, the Region created models to project climate change impacts to water supplies and infrastructure. Generally, climate change is expected to increase temperatures, with little to no change in average rainfall, and increase in water demand due to higher irrigation needs caused by increased temperatures. This project will consolidate septic systems into a larger regional sewer system. Monroe Street directly addresses multiple high and medium priority vulnerabilities related to “Water Supply: Decrease in imported supply” and “Water Demand: Limited ability to meet summer demand” by replacing septic systems with regional sewer infrastructure, thereby protecting the Region’s drinking water supply from contaminants. Optimizing sewer systems is a strategy that helps to adapt to climate change. Many septic systems are failing and contaminating the precious groundwater resources below. By protecting local groundwater supplies, it reduced the need for costly supplemental and imported water supplies that are subject to climate impacts. An additional benefit is there’s an opportunity for the sewage agencies to treat the wastewater to recycled water. As climate change risks water availability for the area, it is important to begin creating new opportunities that can stabilize and secure water.
5 | Does the project contribute to regional water self-reliance?
|  | Yes | No | If yes, please explain below.
The project will abandon degraded septic systems to connect to the region’s sewer collection systems, which protects the groundwater basin from nitrate and pathogen loading, thereby improving the region's water supply reliability and self-reliance (a healthy groundwater basin).
6 | Does the project provide a benefit that meets at least one of the Statewide Priorities as defined in the 2019 IRWM Grant Program Guidelines?
|  | Yes | No | If yes, please identify below.
7 | Will CEQA be completed within 12 months of Final Award?
Yes
NA, project is exempt under CEQA
NA, not a project under CEQA
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
8 | Will all permits necessary to begin construction be acquired within 12 months of Final Award?
Yes
NA, project benefits DAC/EDA/Tribe (minimum 75%), or a Tribe is a local project sponsor
No
C. | WORK PLAN, BUDGET, and SCHEDULE SUMMARY
1 | Project Description: Provide a brief project description summarizing major components, objectives, goals, and intended outcomes/benefits (quantitative and qualitative).
In 2012, U.S. Indian Health Services (IHS) prepared a Preliminary Engineering Report evaluating proposed actions for wastewater management at the Torres-Martinez Band of Cahuilla Indians Avenue 64 housing subdivision. The report recommended construction of a sewer transmission main along Monroe Street to connect to CVWD’s sanitary sewer system. As a follow-on, IHS prepared a 2019 Technical Memorandum with updated information for the project. Septic systems in the Avenue 64 housing subdivision are failing and the lot sizes are insufficient for construction of replacement drainfields. Per the 2019 Technical Memorandum, the Monroe Street project is needed for the protection of public health from the threat of exposure to pathogens in surfacing sewage and for the protection of the Tribe’s drinking water wells from the threat of failed septic systems contaminating groundwater. The Torres-Martinez Band of Cahuilla Indians Avenue 64 housing subdivision consists of 33 Tribal homes, a community park, cemetery, and church all currently on failing septic systems. An onsite sewer collection system within the subdivision has already been constructed through a joint project with the Tribe, IHS, and the US Environmental Protection Agency (EPA). The proposed project would connect the Tribe's new subdivision collection system to the existing CVWD sewer collection pipeline on Monroe Street north of Avenue 62. Approximately one mile of 10-inch VCP sewer main, with manholes located every 500 ft, would be constructed within the Monroe Street right of way and owned by CVWD. It would then be connected to an existing 33-inch VCP sewer main at the intersection of Monroe and Avenue 62. The new subdivision collection system, that is already constructed, entails 1,700 ft of 8-inch PVC sewer main with manholes located every 500 ft within the existing subdivision roads to serve all the homes; this portion was funded by EPA and is not considered part of the proposed project. This project involves removing septic tanks from the perched groundwater, which flows to the local agricultural drainage system and the Salton Sea. The perched aquifer has documented high nitrate levels and septic tanks are currently contributing to this issue. This project would remove failing septic systems that could potentially cause disease by direct contact with sewage that has surfaced and may carry disease vectors. This consolidation project would reduce the potential to contaminate drinking water sources with septic system contaminants such as nitrate.
2 | Budget: Provide cost estimates for each Budget Category listed in the table below. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 1 - Project Budget
Category |  |  | (a) |  | (b) |  | (c) | (c) | (d)
|  |  | Cost Share: Non‐ State Fund Source |  | Requested Grant Amount |  | Other Cost Share (including other State Sources) |  | Total Cost
(a) | Project Administration |  | 16000 |  | 14250 |  | 0 |  | 30250
(b) | Land Purchase/ Easement |  | 0 |  | 0 |  | 0 |  | 0
(c) | Planning/Design /Engineering /Environmental Documentation |  | 16000 |  | 0 |  | 50000 |  | 66000
(d) | Construction/ Implementation |  | 947325 |  | 950000 |  | 0 |  | 1897325
(e) | Grand Total (Sum rows (a) through (d) for each column) |  | 979325 |  | 964250 |  | 50000 |  | 1993575
Note: Provide information or other documentation to support the cost estimate in a separate attachment. Identify the source of all cost share and other funds. If other funds are not used, describe efforts to obtain other funding and/or why other funding sources were not used.
The non-state funding match will be provided by a USDA Rural Development Grant. The cost estimate is based on a August 2019 Technical Memorandum completed by Indian Health Services for the project.
3 | Cost Share Waiver Requested (DAC or EDA)? |  |  |  |  | Yes | No | If yes, continue below:
Cost Share Waiver Justification: Describe what percentage of the proposed project area encompasses a DAC/EDA, how the community meets the definition of a DAC/EDA, and the need of the DAC/EDA that the project addresses. In order to receive a cost share waiver, the applicant must demonstrate that the project will provide benefits (minimum 25% by population or geography) that address a need of a DAC and/or EDA.
The total cost associated with the ECVSSC – Monroe Street project is $1,993,575. Of these total costs, $964,250 is being requested for grant funding (48%) through the IRWM Grant Program. The $979,325 funding match (49%) will be provided by CVWD staff labor hours and a USDA Rural Development grant; a partial cost share waiver is requested for this project because the funding match is not fully 50%. The Avenue 64 Housing Subdivision is located in a 2016 tract with a median household income (MHI) of $31,750 per DWR's DAC Mapping Tool. As their MHI is less than 60% of the statewide MHI of $38,272, the project area is severely DAC. This project is targeted to help improve the safety of the community by removing the failing septic systems that are causing sewage to surface in the backyards of the homes in the subdivision and will also reduce the nitrogen and pathogen loading from these septic systems to their groundwater basin. The latter is important as the system relies on a drinking water well that is within the subdivision and thus in close proximity to the failing septic systems.
4 | Schedule: Include reasonable estimates of the start and end dates for each Budget Category listed in Table 1 - Project Budget. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
Table 2 - Project Schedule
Category |  |  |  |  | (a) Start Date |  |  | (b) End Date
(a) | Direct Project Administration |  |  |  | 2020-04-15 |  |  | 2022-04-22
(b) | Land Purchase/ Easement |  |  |  | N/A |  |  | N/A
(c) | Planning/Design/Engineering/Environmental Documentation |  |  |  | 2019-08-01 |  |  | 2020-10-01
(d) | Construction/ Implementation |  |  |  | 2020-10-02 |  |  | 2022-01-14
D. | OTHER PROJECT INFORMATION
1 | Provide a narrative for project justification. If applicable, include references to supporting documentation such as models, studies, engineering reports, etc. Include any other information that supports the justification for this project, including how the project can achieve the claimed level of benefits.
CVWD provides water related services including wastewater collection and treatment throughout a region covering approximately 1,000 square miles, mostly within the Coachella Valley in Riverside County, California. In the East Coachella Valley region of its service area, there are a number of rural communities that are not connected to CVWD’s sanitary sewer collection system. These communities are classified as disadvantaged communities (DACs) with median household incomes (MHIs) less than 80 percent of the California statewide MHI and depend on onsite wastewater treatment systems (OWTS) and/or septic systems. CVWD has evaluated the consolidation of individual septic systems within the Eastern Coachella Valley into CVWD’s sanitary sewer system. CVWD partnered with its DAC infrastructure Task Force to evaluate its Sanitation Priorities in coordination with other water and wastewater infrastructure projects in the Eastern Coachella Valley. A total of 89 septic systems were identified for potential sewer consolidation in the East Coachella Valley, including permitted and unpermitted systems. Approximately 55 out of the 89 individual septic systems identified for consolidation were grouped into 18 DAC centered projects and masterplan projects. The ECVSSC-Monroe Street project ranked fourth based on proximity to existing sewers, time to implement, costs, regional sewer system, known issues and population. (Reference: CVWD Sanitation Priorities Task Order Technical Memorandum, by Woodard & Curran, August 2019) The three projects ranked higher will still be completed; however, the Monroe Street project was chosen to be included in this grant application package as it was the farthest along in the planning and design process. As discussed in the CVWD Sewer Main Extension to Avenue 64 Housing Subdivision preliminary engineering report (prepared by IHS in May 2012) and updated in a August 2019 Technical Memorandum by IHS, the Avenue 64 housing subdivision consists of 33 Tribal homes, a community park, cemetery, and church all currently on a failing septic system. A sewer collection system and transmission pipeline need to be built to connect to CVWD's sewer collection system. The report states the need for the project as health, sanitation and security reasons. The project would remove failing septic systems that could potentially cause disease by direct contact, fostering disease carrying vectors, contaminating drinking water sources with different pollutants.
2 | Project Benefits Table:
Table 3 - Project Benefits
Anticipated Useful Life of Project (years): |  |  |  |  | 50
Primary (Required)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Secondary (Optional)
Type of Benefit Claimed: | [6 empty] | Benefit Units*:
Physical Benefits (At project completion or lifetime, as appropriate)
(a) |  |  | (b) |  |  |  | (c)
Benefit |  |  | Added Physical Benefit Description |  |  |  | Quantitative Benefit
Primary |  |  | Raw wastewater has a value of 45 mg/L and after secondary treatment will be approx 25 mg/L |  |  |  | Approx. 20 mg/L of nitrate will be reduced in discharges to the groundwater basin
Secondary |  |  | Project will treat and recharge 19 AFY |  |  |  | 19 AFY
Qualitative Benefits (For Decision Support Tools, please describe non-physical benefits.)
Comments: [Include narrative on additional benefits, as warranted.]
The primary benefit to this project is the removal of nitrate, an AB 1249 contaminant, from the water that is currently discharged to the Indio Subbasin and ultimately to the Salton Sea. This will help to protect and improve groundwater quality by reducing bacteria and nitrate discharged from failing septic systems. Raw wastewater has a typical total nitrogen value of 45 mg/L and after secondary treatment the total nitrogen value will be less than 25 mg/L (based on CVWD effluent monitoring results for WRP-4; note that WRP-4 does not provide denitrification like Horton WWTP). This ultimately removes 20 mg/L of nitrogen, of which nitrate is a component, from the water currently discharged to the Indio Subbasin. Consolidating septic systems with water quality issues into municipal sewer collection systems is typically the most cost-effective way to reduce groundwater quality degradation (nitrate and pathogen loading) to these DACs. The secondary benefit of this project is that it will treat and recharge 19 AFY of treated wastewater to the Indio Subbasin. This project will also allow wastewater that is currently discharged directly to the groundwater basin to be collected and used in a future recycled water project, which will reduce the amount of imported water needed in the region.
* | DWR may require applicant to convert or modify Benefit Claimed and/or Benefit Units. Where applicable, select one of the following units that corresponds to the benefit claimed: • For water supply produced, saved, or recycled, enter acre-feet per year (AFY) • For water quality, enter constituent concentration reduced in mg/L • For flood damage reduction, enter inundated acres reduced in acres • For habitat improved, restored or protected, enter habitat restored in acres • For fishery benefits, enter increased fishery flow rate in cubic feet per second (cfs) • For species protection, enter number of species benefited
3 | Does the proposed project provide benefits to multiple IRWM regions [or funding areas]? If the project is located in another funding area, please provide the information requested in the 2019 Guidelines, Section 1.A.
|  | Yes | No | If yes, provide a description of the benefits to the various regions.
N/A
4 | Provide a narrative on cost considerations. For example, were other alternatives to achieve the same types and amounts of physical benefits as the proposed project evaluated? Provide a justification as to why the project was selected (e.g., if the proposed project is not the lowest cost alternative, why is it the preferred alternative? Are there any other advantages that the proposed project provides from a cost perspective?)
The 2012 preliminary engineering report prepared by Indian Health Services considered 3 project options. Option #1 included a new 8-inch PVC sewer main along Monroe Street, owned and maintained by the Tribe. Option #2 included a new 10-inch VCP sewer main owned and maintained by CVWD. Option #3 included a new 8-inch PVC variable grade sewer owned and operated by the Tribe. Option #2 was selected as the recommended option, although it was not the most cost-effective since it results in a better long-term solution for both CVWD and the Tribe. Option #2 presents the highest capital cost of the options but is the lowest O&M cost and least amount of burden to the Tribe and allows regional expansion of the sewer system.
5 | a. Does the project address a contaminant listed in AB 1249?
|  | Yes | No | If yes, complete parts b and c:
b. Describe how the project helps address the contamination.
The project will reduce nitrate loading by approximately 20 mg/L to the Indio groundwater basin and ultimately to the Salton Sea. Wastewater that is currently discharged to the groundwater basin via septic system will be collected and sent to CVWD's WRP4.
c. Does the project provide safe drinking water to a small disadvantaged community?
|  | Yes | No | If yes, provide an explanation on how the project benefits a small disadvantaged community as defined in the 2019 IRWM Guidelines.
N/A
6 | Does the project provide safe, clean, affordable, and accessible water adequate for human consumption, cooking, and sanitary purposes (consistent with AB 685) to meet a specific need(s) of a community?
|  | Yes | No | If yes, please describe.
N/A
7 | Does the project employ new or innovative technologies or practices, including decision support tools that support the integration of multiple jurisdictions, including, but not limited to, water supply, flood control, land use, and sanitation?
|  | Yes | No | If yes, please describe.
N/A
8 | If the project provides benefits (75% by population or geography) to a DAC, explain the need of the DAC and how the project will address the described need. Explain how the area/community meets the definition of a DAC.
The Avenue 64 Housing Subdivision is located in a 2016 tract with a median household income (MHI) of $31,750 per DWR's DAC Mapping Tool. As their MHI is less than 60% of the statewide MHI of $38,272, the project area is 100% severely DAC. This project is targeted to help improve the safety of the community by removing the failing septic systems that are causing sewage to surface in the backyards of the homes in the subdivision and will also reduce the nitrogen and pathogen loading from these septic systems to their groundwater basin. The latter is important as the system relies on a drinking water well that is within the subdivision and thus in close proximity to the failing septic systems.
9 | If the project provides benefits (75% by population or geography) to an EDA, explain the need of the EDA and how the project will address the described need. Explain how the area/community meets the definition of an EDA.
N/A
10 | If the project provides benefits (75% by population or geography) to a Tribe or a Tribe is the sponsor of the project, explain the need of the Tribe and how the project will address the described need.
The project provides 100% (by population and geography) benefits to the Torres Martinez Band of Cahuilla Indians. The Avenue 64 housing subdivision consists of 33 Tribal homes, a community park, cemetery, and church all currently on a failing septic system. A 10-inch VCP gravity sewer main is proposed by CVWD to connect to the existing sewer collection system on Monroe Street. The project addresses the sanitation needs of the Torres Martinez Band of Cahuilla Indians by connecting them to CVWD's sanitary sewer system so that they are no longer relying on failing septic systems that can cause various health hazards to the residents of the housing subdivision.
11 | Does the project sponsor have legal access rights, easements, or other access capabilities to the property to implement the project?
|  | Yes | If yes, please describe.
|  | NA | If NA, please describe why physical access to a property is not needed.
|  | No | If no, please provide a clear and concise narrative with a schedule to obtain necessary access.
The project will occur in the public right of way on Monroe Street and onTorres Martinez Desert Cahuilla Indians tribal land. An encroachment permit will be filed with the County of Riverside for the work in the public right of way. For the portion of the project on tribal land, there is a 2017 agreement between CVWD and the tribe (Special Sanitation Installation Agreement between CVWD and Torres Martinez DCI. Riverside County No. 2017-0345827)
E. | ENVIRONMENTAL
1 | Please fill out the CEQA Timeline Table below, if applicable:
Table 4 - CEQA Timeline
CEQA STEP |  |  |  |  | COMPLETE? (y/n) |  |  | ESTIMATED DATE TO COMPLETE
|  | Initial Study |  |  | N |  |  | 2013-04-01
|  | Notice of Preparation |  |  | N |  |  | N/A
|  | Draft EIR/MND/ND |  |  | N |  |  | N/A
|  | Public Review |  |  | N |  |  | N/A
|  | Final EIR/MND/ND |  |  | N |  |  | N/A
|  | Adoption of Final EIR/MND/ND |  |  | N |  |  | N/A
|  | Notice of Determination |  |  | N |  |  | 2020-05-01
a. If additional explanation or justification of the timeline is needed, please describe below (optional).
In April 2013, a Biological Assessment for Plants and Animals, Botany and Wildlife Report for the Torres Martinez Indian Reservation Sewer and Water Line Improvement Project by L&L Environmental, Inc, and an Archaeological Record Search and Survey Report for the for the Torres Martinez Water and Sewer Project by L&L Environmental, Inc. were completed. Notice of Exemption for this project was completed in August 26, 2019. A Notice of Determination will be filed with the State Clearinghouse and Riverside County clerk immediately after grant award.
2 | Permit Acquisition Plan:
List all permits needed to complete the project. If the project does not provide benefits to a DAC, EDA, or Tribe (min 75%), all permits needed to begin construction must be acquired within 12 months of Final Award.
No. |  | Type of Permit |  |  | Permitting Agency |  |  | Date Acquired or Anticipated
1 |  | Encroachment, Road and Construction Permits |  |  | County of Riverside |  |  | 2020-07-30
2 |  | Permit to Construct |  |  | South Coast Air Quality Management |  |  | 2020-07-30
3 |  | Fugutive Dust Control Plan |  |  | South Coast Air Quality Management |  |  | 2020-07-30
4 |  | General Permit for Construction Discharges |  |  | RWQCB, Colorado River |  |  | 2020-07-30
5
6
n.
For each permit not yet acquired, describe the following:
No. |  | a. Actions taken to date (include dates of any key meetings, consultations, submittals, etc.) |  |  |  | b. Any issues or obstacles that may delay acquisition of permit
1
2
3
4
5
n.
3 | Permitting Checklist: This checklist is provided as a courtesy for documentation purposes. Not all permits which may apply are listed. (Required for Pre-Application Material Submittal; not required for Final Application Submittal)
a. | Does the project involve any activities that may affect federally or state listed threatened or endangered species or their critical habitat that are known, or have a potential, to occur on-site, in the surrounding area, or in the service area? (i.e. Federal Endangered Species Act Section 7 Consultation and Incidental Take Authorization and Section 10 Incidental Take Permit, California Endangered Species Act Permit, and/or ESA & CESA Consistency Determination)
|  | Yes | No | If yes, please explain:
N/A
b. | Would the proposed project work in, over, or under navigable waters of the US or discharge dredged or fill material in waters of the US? (i.e. Rivers & Harbors Act Section 10 Permit and/or Clean Water Act Section 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
c. | Will the proposed project have the potential to affect historical, archaeological, or cultural resources? (i.e. National Historic Preservation Act and/or State Historic Preservation Officer Consultation)
|  | Yes | No | If yes, please explain:
N/A
d. | Will the proposed project discharge into a water of the US? (i.e. Clean Water Act Section 401 and/or 404 Permit)
|  | Yes | No | If yes, please explain:
N/A
e. | Will the proposed project divert the natural flow of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
f. | Will the proposed project change the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
g. | Will the proposed project use any material from the bed, channel, or bank of a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement)
|  | Yes | No | If yes, please explain:
N/A
h. | Will the proposed project deposit or dispose of debris, waste, or other material containing crumbled, flaked, or ground pavement where it can pass into a river, stream, or lake? (i.e. Lake or Streambed Alteration Agreement/National Pollutant Discharge Elimination System Permit/Waste Discharge Requirements Permit)
|  | Yes | No | If yes, please explain:
N/A
i. | For water supply projects, do you need to obtain a water right? (Water Rights Permit)
|  | Yes | No | If yes, please explain:
N/A
j. | Is the proposed project within the defined coastal zone? (Coastal Development Permit)
|  | Yes | No | If yes, please explain:
N/A

## Answers (hidden)
A. PROJECT INFORMATION
1
2
3
4
5
6
7
8
9

## List Values (hidden)
Eligible Applicant Type | IRWM Regions | Project Type | Benefit Claimed | Benefit Units | Statewide Priorities
| American River Basin |  |  |  | 1. Make Conservation a California Way of Life
Public Agency | Antelope Valley | Conjunctive use | Ecosystem Restoration | acre(s) | 2. Increase Regional Self-Reliance and Integrated Water Management Across All Levels of Government
Non-profit Organization | Anza Borrego Desert | Decision support tool | Ecosystem/Freshwater habitat | AFY | 3. Achieve the Co-Equal Goals for the Delta
Public Utility | Coachella Valley | Groundwater aquifer cleanup | Fishery Improvements | cfs | 4. Protect and Restore Important Ecosystems
Federally Recognized Indian Tribe | Cosumnes, American, Bear, Yuba (CABY) | Other | Flood Damage Reduction | mg/L | 5. Manage and Prepare for Dry Periods
Indian Tribe listed on the Native American Heritage Commission’s California Tribal Consultation List | East Contra Costa County | Recharge project | Flood Management | Other | 6. Expand Water Storage Capacity and Improve Groundwater Management
Mutual Water Company | East Stanislaus | Stormwater management | Groundwater Recharge |  | 7. Provide Safe Water for All Communities
| Eastern San Joaquin | Surface storage | Habitat Restoration |  | 8. Increase Flood Protection
| Fremont Basin | Underground water storage | Operational Efficiency |  | 9. Increase Operational and Regulatory Efficiency
| Greater Los Angeles County | Water conservation | Grant Admin |  | 10. Identify Sustainable and Integrated Financing Opportunities
| Greater Monterey County | Water conveyance facility | Reduce Groundwater Pumping |  |  | ListBox Option
| Imperial | Water desalination | Flood Protection
| Inyo-Mono | Water quality | Stormwater Management
| Kaweah River Basin | Water recycling | Streamflow Restoration
| Kern County | Water reuse | Water Conservation
| Kings Basin Water Authority | Watershed project | Water Quality
| Lahontan Basins | Water-use efficiency | Water Quality - Groundwater
| Madera |  | Water Quality - Sediment
| Merced |  | Water Quality - Surface Water
| Mojave |  | Water Supply - Groundwater
| Mokelumne/Amador/Calaveras (MAC) |  | Water Supply - Recycled Water
| Monterey Peninsula, Carmel Bay, So. Monterey Bay |  | Water Supply - Surface Water
| North Coast |  | Water Supply Reliability
| North Sacramento Valley |  | Other
Pajaro River Watershed
Poso Creek
San Diego
San Francisco Bay Area
San Gorgonio
San Luis Obispo
Santa Ana River Watershed
Santa Barbara County
Santa Cruz County
South Orange County Watershed Management Area
Southern Sierra
Tahoe-Sierra
Tule River Basin
Tuolumne-Stanislaus
Upper Feather River Watershed
Upper Pit River Watershed
Upper Sacramento-McCloud
Upper Santa Clara River
Upper Santa Margarita
Watersheds Coalition of Ventura County
Westside (Yolo, Solano, Napa, Lake, Colusa)
Westside-San Joaquin
Yosemite-Mariposa
Yuba County